## Slide 1: Software Project Management

## Slide 2: Introduction
What does Plan-and-Document do instead of
  User stories?
  Points?
  Velocity?
How does a project manager estimate costs?
Make a Schedule?

## Slide 3: Project Management Process
Why do we need project management?
Why can't we just follow one of the software development process and be left alone?
All projects – small and large – need project management.
Process:
  Planning
  Organizing
  Monitoring of status
  Adjustment

## Slide 4: Software Project Management Process
Project
Planning
Project
Organizing
Project
Monitoring
Project
Adjusting
Looks sequential but may be iterative.

## Slide 5: Success criteria
Deliver the software to the customer at the agreed time.
Keep overall costs within budget.
Deliver software that meets the customer’s expectations.
Maintain a happy and well-functioning development team.

## Slide 6: Activities vs. Tasks
Activity: A major unit of work with precise dates that consists of smaller activities or tasks
Task: Smallest unit of work subject to management.

## Slide 7: Monitoring
Need regularly tracking a project to ensure that the it is headed in the right direction.
Three main components of project monitoring:
  Status collection
  Analysis
  Presentation and communication

## Slide 8: Milestones and deliverables
Milestones are points in the schedule against which you can assess progress
Deliverables are work products that are delivered to the customer

## Slide 9: Adjusting
As soon as the project status suggests potential problem, we must not be afraid to make changes.
Three main areas of adjustments are :
  Resources
  Schedule
  Project content

## Slide 10: Planning

## Slide 11: Project Planning
Software project planning involves deciding
  what tasks need to be done
  in what order to do the tasks
  what resources are required to accomplish the tasks

## Slide 12: How Long?
Need to determine how long it will take to complete the project
Solution: Use divide and conquer

## Slide 13: Planning Process
Identify the tasks
Hierarchically organize the tasks
Identify dependencies between tasks
Map tasks onto time

## Slide 14: Work Breakdown Structure

## Slide 15: Work Breakdown Structure (WBS)
Break activities into tasks and large tasks into small tasks
Find identifiable parts of the tasks
Finding deliverables and milestones that can be used to measure progress

## Slide 16: Developing a WBS
Must be a tree structure
Every task and deliverable must be understandable and unambiguous
Every task must have a completion criteria
All deliverables must identified
Completion of all subtasks must result in completion of task

## Slide 17: Top Down WBS
Specify all activities required for the entire project to be finished.
Determine all tasks required to complete each activity.
If necessary, specify sub-activities required to complete each task.
Continue in this way until you have adequately detailed your project.

## Slide 18: Brainstorming WBS
On a single list, write any activities you think will have to be performed for your project.
Then study the list and group activities into a few major categories with common characteristics .
If appropriate, group identified activities into higher level activities.
Review

## Slide 19
Prepare Report
1.0 Prepare draft report
2.0 Review draft report
3.0 Prepare final report
  3.1 Write final report
  3.2 Print final report
Review
Draft Report
Prepare
Report
Review
Draft Report
Review
Final Report
Print
Final Report
Write
Final Report
Prepare Report
Prepare
Draft Report
Review
Draft Report
Prepare
Final Report
Write
Final Report
Print
Final Report
Org-Chart Format
Outline Format
Bubble Format

## Slide 20: Dependencies and Scheduling
Notes: start here

## Slide 21: PERT
Creates a graph that shows the dependencies among the tasks
Purpose
  Identify the critical path
  Determine slack time

## Slide 22: Example
Task | Time to Complete Task | Dependencies
A | 8 | 
B | 10 | 
C | 8 | A, B
D | 9 | A
E | 5 | B
F | 3 | C, D
G | 2 | D
H | 4 | F, G
I | 3 | E, F

## Slide 23: Activity Diagram
E
t=5
A
t=8
B
t=10
C
t=8
D
t=9
F
t=3
G
t=2
H
t=4
I
t=3
Start
End
A | 8 | 
B | 10 | 
C | 8 | A, B
D | 9 | A
E | 5 | B
F | 3 | C, D
G | 2 | D
H | 4 | F, G
I | 3 | E, F

## Slide 24: Analyzing Activity Diagrams
Determination of critical paths
  Also called forward path analysis
Determination of slack times
  Also called back path analysis

## Slide 25: Definitions
Earliest start date (ES): The earliest date you can start an activity
Earliest finish date (EF): The earliest date you can finish an activity
Latest start date (LS): The latest date you can start an activity and still finish the project in the shortest time
Latest finish date (LF): The latest date you can finish an activity and still finish the project in the shortest time.

## Slide 26: Rules for computing start and finish times
After a node is finished, we can proceed to the next node(s) that is (are) reachable via a transition from the current node.
To start a node, all nodes from which transitions to that node are possible must be complete.

## Slide 27: Forward Pass
Goal is the determination of critical paths
Compute earliest start and finish dates for each activity
Start at the beginning of the project and determine how fast you can complete the activities along each path until you reach the final project milestone

## Slide 28
Task | Earliest Start | Earliest Finish
A | 0 | 8
B | 0 | 10
C | 10 | 18
D | 8 | 17
E | 10 | 15
F | 18 | 21
G | 17 | 19
H | 21 | 25
I | 21 | 24
E
t=5
A
t=8
B
t=10
C
t=8
D
t=9
F
t=3
G
t=2
H
t=4
I
t=3
Start
End

## Slide 29: Finding the Critical Path
Critical path is the set of tasks that determines the shortest possible completion time
Algorithm
  Start with the nodes with the latest completion time and mark them as critical
  Select the predecessors of these nodes and mark them as critical
  Repeat until reaching the starting node

## Slide 30
Task | Earliest Start | Earliest Finish
A | 0 | 8
B | 0 | 10
C | 10 | 18
D | 8 | 17
E | 10 | 15
F | 18 | 21
G | 17 | 19
H | 21 | 25
I | 21 | 24
E
t=5
A
t=8
B
t=10
C
t=8
D
t=9
F
t=3
G
t=2
H
t=4
I
t=3
Start
End
Critical Path

## Slide 31: Slack Time
Tasks on the critical path have to be started as early as possible or the whole project will be delayed
Tasks not on the critical path have some flexibility as to when they are started
Flexibility is called slack time
Process
  Compute latest start and finish times
  Start at the end of your project and determine how late each activity can be started so that you still finish the project at the earliest possible date.
Notes: start here

## Slide 32
Task | Earliest Finish | Latest Start | Latest Finish
A | 8 | 1 | 9
B | 10 | 0 | 10
C | 18 | 10 | 18
D | 17 | 9 | 18
E | 15 | 17 | 22
F | 21 | 18 | 21
G | 19 | 19 | 21
H | 25 | 21 | 25
I | 24 | 22 | 25
E
t=5
A
t=8
B
t=10
C
t=8
D
t=9
F
t=3
G
t=2
H
t=4
I
t=3
Start
End
Project Duration: 25

## Slide 33: Slack Time
Task | Latest Start | Earliest Start | Slack Time
A | 1 | 0 | 1
B | 0 | 0 | 0
C | 10 | 10 | 0
D | 9 | 8 | 1
E | 17 | 10 | 7
F | 18 | 18 | 0
G | 19 | 17 | 2
H | 21 | 21 | 0
I | 22 | 21 | 1
Slack Time = Latest Start – Earliest Start

## Slide 34: Bar Charts
Show the schedule as activities or resources against time.
Usually called a Gantt chart
Modern Gantt charts show dependencies between tasks.

## Slide 35: Tasks, durations, and dependencies
Task | Duration (days) | Dependencies
T1 | 10 | 
T2 | 15 | 
T3 | 15 | T1 (M1)
T4 | 10 | 
T5 | 10 | T2, T4 (M3)
T6 | 5 | T1, T2 (M4)
T7 | 20 | T1 (M1)
T8 | 25 | T4 (M2)
T9 | 15 | T3, T6 (M5)
T10 | 15 | T7, T8 (M6)
T11 | 10 | T9 (M7)
T12 | 10 | T10, T11 (M8)

## Slide 37: Estimation
Notes: Start here

## Slide 38: Project Effort Estimation
Units of effort = a + b (size)c + Σ(factors)
Most of the estimating techniques use some form of this general formula
The most commonly used product attribute for cost estimation is code size.

## Slide 39: Estimate Accuracy

## Slide 40: COCOMO Estimation model
An empirical model based on project experience.
Steps
  Select a project mode
  Estimate the size of the project
  Review cost-drivers to estimate the impact each will have on the project
  Insert estimated values into effort formula for chosen mode

## Slide 41: Lines of Code (LOC)
Lines of source code /programmer-months
Based on
  Experience
  Size of previous project
  Size of competitor solution
  Breaking down the project into smaller pieces and estimating each of the smaller pieces
Problems
  Not a simple relationship between program statements and lines of code
  Comparing across programming languages can be misleading

## Slide 42: Function Points
Function points in a program are computed by measuring or estimating
  External inputs
  Eternal outputs
  External inquiry
  Internal logical files
  External interface files
These various measurements are weighted based on their complexity
Productivity is measured by the number of function points per person-months
Notes: start here

## Slide 43: Function Point Weights
 | Simple | Average | Complex
Inputs | 3 | 4 | 6
Outputs | 4 | 5 | 7
Inquiries | 3 | 4 | 6
Files | 7 | 10 | 15
Interfaces | 5 | 7 | 10

## Slide 44: OO Effort Estimation
Developed by Lorenz and Kidd for OO projects
Steps
  Estimate the number of classes
  Categorize the types of interfaces and assign a weight
  Multiply classes by weight and add to original sum to get a new estimate of total classes
  Multiply by a productivity estimate of number of person-days required to develop a class

## Slide 45: Issues with Size Metrics
Ignore reuse, code generators and other tools
Quality is not considered

## Slide 46: Risk Management

## Slide 47: Risk management
Risk management is concerned with identifying risks and drawing up plans to minimize their effect on a project.
A risk is a probability that some adverse circumstance will occur
  Project risks
  Product risks
  Business risks

## Slide 48: The risk management process
Risk identification
  Identify project, product and business risks
Risk analysis
  Assess the likelihood and consequences of these risks
Risk planning
  Draw up plans to avoid or minimize the effects of the risk
Risk monitoring
  Monitor the risks throughout the project

## Slide 49: Risk planning
Consider each risk and develop a strategy to manage that risk.
Avoidance strategies
Minimization strategies
Contingency plans

## Slide 50: P and D vs. Agile Requirements and Schedule/Cost Estimation